## task_groups
code | name | Description | sequence
10 | Pre-Construction | Design, permitting, budgeting, scheduling, and long-lead procurement activities before physical work begins | 1
20 | Site Preparation | Clearing, grading, erosion control, and temporary utility setup to prepare the site for foundation work. | 2
30 | Foundation | Excavation, formwork, reinforcement, and concrete work to establish the structural base of the building. | 3
40 | Framing | Construction of walls, floors, and roof structure to define the building’s shape and layout. | 4
50 | Exterior Envelope | Installation of sheathing, weather barrier, cladding, and exterior finishes to close in the structure. | 5
60 | MEP Roughs & Dry-In | Installation of mechanical, electrical, and plumbing systems (rough-ins), followed by insulation and drywall to dry-in the interior. | 6
70 | Interior Finishes | Completion of interior elements such as flooring, trim, painting, cabinetry, and final fixtures. | 7
80 | Landscaping & Exterior | Exterior site work including driveways, patios, landscaping, fencing, and exterior accessories. | 8
90 | Closeout | Final inspections, punch list completion, cleaning, and preparation for client turnover. | 9

## task_master
code | name | description | is_active | task_group_code
10.100 | Architectural Design |  | TRUE | 10
10.200 | Engineering Design (Structural/MEP) |  | TRUE | 10
10.300 | Permits & Approvals |  | TRUE | 10
10.400 | Budgeting & Financing Setup |  | TRUE | 10
10.500 | Project Planning & Scheduling |  | TRUE | 10
10.600 | Procurement of Long-Lead Materials |  | TRUE | 10
10.700 | Inspection (Pre-Construction Site) |  | TRUE | 10
20.100 | Site Survey & Soil Testing |  | TRUE | 20
20.200 | Site Clearing & Excavation |  | TRUE | 20
20.300 | Temporary Utilities Setup |  | TRUE | 20
20.400 | Grading & Site Preparation |  | TRUE | 20
20.500 | Erosion / Tree Control |  | TRUE | 20
20.600 | Inspection (Erosion / Tree Protection) |  | TRUE | 20
30.100 | Formwork for Foundation |  | TRUE | 30
30.200 | Rebar Installation |  | TRUE | 30
30.300 | Inspection (Footings) |  | TRUE | 30
30.400 | Underground Plumbing |  | TRUE | 30
30.500 | Inspection (Underground Plumbing) |  | TRUE | 30
30.600 | Concrete Pouring (Footings & Slab) |  | TRUE | 30
30.700 | Foundation Walls |  | TRUE | 30
30.800 | Foundation Waterproofing |  | TRUE | 30
30.900 | Inspection (Slab) |  | TRUE | 30
40.100 | Framing – Walls & Floors |  | TRUE | 40
40.200 | Framing – Roof |  | TRUE | 40
40.300 | Inspection (Rough Framing) |  | TRUE | 40
50.100 | Sheathing & Weather Barrier |  | TRUE | 50
50.200 | Siding |  | TRUE | 50
50.300 | Window Installation |  | TRUE | 50
50.400 | Roofing Installation |  | TRUE | 50
50.500 | Exterior Painting & Cladding |  | TRUE | 50
50.600 | Inspection (Roof Sheathing) |  | TRUE | 50
60.100 | Plumbing Rough-in |  | TRUE | 60
60.200 | Inspection (Rough Plumbing) |  | TRUE | 60
60.300 | Electrical Rough-in |  | TRUE | 60
60.400 | Inspection (Rough Electrical) |  | TRUE | 60
60.500 | HVAC Rough-in |  | TRUE | 60
60.600 | Inspection (Rough HVAC) |  | TRUE | 60
60.700 | Fire Sprinkler Installation |  | TRUE | 60
60.800 | Insulation |  | TRUE | 60
60.900 | Inspection (Insulation) |  | TRUE | 60
60.1000 | Drywall Installation |  | TRUE | 60
60.1100 | Inspection (Energy Code Compliance) |  | TRUE | 60
70.100 | Interior Painting |  | TRUE | 70
70.200 | Flooring Installation |  | TRUE | 70
70.300 | Cabinetry & Trim |  | TRUE | 70
70.400 | Appliance Installation |  | TRUE | 70
70.500 | Plumbing Fixtures |  | TRUE | 70
70.600 | Electrical Fixtures |  | TRUE | 70
70.700 | HVAC Finish |  | TRUE | 70
70.800 | Rough Clean |  | TRUE | 70
70.900 | Drywall Touchup |  | TRUE | 70
70.1000 | Paint Touchup |  | TRUE | 70
70.1100 | Final Clean |  | TRUE | 70
80.100 | Landscaping |  | TRUE | 80
80.200 | Patios |  | TRUE | 80
80.300 | Fencing |  | TRUE | 80
80.400 | Pool |  | TRUE | 80
80.500 | Driveway |  | TRUE | 80
90.100 | Inspection (Final MEP Systems) |  | TRUE | 90
90.200 | Inspection (Final Building) |  | TRUE | 90
90.300 | Inspection (Final Site / Grading) |  | TRUE | 90
90.400 | Inspection (Certificate of Occupancy) |  | TRUE | 90

## template_tasks
template_id | task_code | name | description
0197e29a-d4cd-7d3b-b1b1-f65b2bd20220 | 10.100 | Architectural Design
0197e29a-d4cd-7d3b-b1b1-f65b2bd20220 | 10.200 | Engineering Design (Structural/MEP)
0197e29a-d4cd-7d3b-b1b1-f65b2bd20220 | 10.300 | Permits & Approvals
0197e29a-d4cd-7d3b-b1b1-f65b2bd20220 | 10.400 | Budgeting & Financing Setup
0197e29a-d4cd-7d3b-b1b1-f65b2bd20220 | 10.500 | Project Planning & Scheduling
0197e29a-d4cd-7d3b-b1b1-f65b2bd20220 | 10.600 | Procurement of Long-Lead Materials
0197e29a-d4cd-7d3b-b1b1-f65b2bd20220 | 10.700 | Inspection (Pre-Construction Site)
0197e29a-d4cd-7d3b-b1b1-f65b2bd20220 | 20.100 | Site Survey & Soil Testing
0197e29a-d4cd-7d3b-b1b1-f65b2bd20220 | 20.200 | Site Clearing & Excavation
0197e29a-d4cd-7d3b-b1b1-f65b2bd20220 | 20.300 | Temporary Utilities Setup
0197e29a-d4cd-7d3b-b1b1-f65b2bd20220 | 20.400 | Grading & Site Preparation
0197e29a-d4cd-7d3b-b1b1-f65b2bd20220 | 20.500 | Erosion / Tree Control
0197e29a-d4cd-7d3b-b1b1-f65b2bd20220 | 20.600 | Inspection (Erosion / Tree Protection)
0197e29a-d4cd-7d3b-b1b1-f65b2bd20220 | 30.100 | Formwork for Foundation
0197e29a-d4cd-7d3b-b1b1-f65b2bd20220 | 30.200 | Rebar Installation
0197e29a-d4cd-7d3b-b1b1-f65b2bd20220 | 30.300 | Inspection (Footings)
0197e29a-d4cd-7d3b-b1b1-f65b2bd20220 | 30.400 | Underground Plumbing
0197e29a-d4cd-7d3b-b1b1-f65b2bd20220 | 30.500 | Inspection (Underground Plumbing)
0197e29a-d4cd-7d3b-b1b1-f65b2bd20220 | 30.600 | Concrete Pouring (Footings & Slab)
0197e29a-d4cd-7d3b-b1b1-f65b2bd20220 | 30.700 | Foundation Walls
0197e29a-d4cd-7d3b-b1b1-f65b2bd20220 | 30.800 | Foundation Waterproofing
0197e29a-d4cd-7d3b-b1b1-f65b2bd20220 | 30.900 | Inspection (Slab)
0197e29a-d4cd-7d3b-b1b1-f65b2bd20220 | 40.100 | Framing – Walls & Floors
0197e29a-d4cd-7d3b-b1b1-f65b2bd20220 | 40.200 | Framing – Roof
0197e29a-d4cd-7d3b-b1b1-f65b2bd20220 | 40.300 | Inspection (Rough Framing)
0197e29a-d4cd-7d3b-b1b1-f65b2bd20220 | 50.100 | Sheathing & Weather Barrier
0197e29a-d4cd-7d3b-b1b1-f65b2bd20220 | 50.200 | Siding
0197e29a-d4cd-7d3b-b1b1-f65b2bd20220 | 50.300 | Window Installation
0197e29a-d4cd-7d3b-b1b1-f65b2bd20220 | 50.400 | Roofing Installation
0197e29a-d4cd-7d3b-b1b1-f65b2bd20220 | 50.500 | Exterior Painting & Cladding
0197e29a-d4cd-7d3b-b1b1-f65b2bd20220 | 50.600 | Inspection (Roof Sheathing)
0197e29a-d4cd-7d3b-b1b1-f65b2bd20220 | 60.100 | Plumbing Rough-in
0197e29a-d4cd-7d3b-b1b1-f65b2bd20220 | 60.200 | Inspection (Rough Plumbing)
0197e29a-d4cd-7d3b-b1b1-f65b2bd20220 | 60.300 | Electrical Rough-in
0197e29a-d4cd-7d3b-b1b1-f65b2bd20220 | 60.400 | Inspection (Rough Electrical)
0197e29a-d4cd-7d3b-b1b1-f65b2bd20220 | 60.500 | HVAC Rough-in
0197e29a-d4cd-7d3b-b1b1-f65b2bd20220 | 60.600 | Inspection (Rough HVAC)
0197e29a-d4cd-7d3b-b1b1-f65b2bd20220 | 60.700 | Fire Sprinkler Installation
0197e29a-d4cd-7d3b-b1b1-f65b2bd20220 | 60.800 | Insulation
0197e29a-d4cd-7d3b-b1b1-f65b2bd20220 | 60.900 | Inspection (Insulation)
0197e29a-d4cd-7d3b-b1b1-f65b2bd20220 | 60.1000 | Drywall Installation
0197e29a-d4cd-7d3b-b1b1-f65b2bd20220 | 60.1100 | Inspection (Energy Code Compliance)
0197e29a-d4cd-7d3b-b1b1-f65b2bd20220 | 70.100 | Interior Painting
0197e29a-d4cd-7d3b-b1b1-f65b2bd20220 | 70.200 | Flooring Installation
0197e29a-d4cd-7d3b-b1b1-f65b2bd20220 | 70.300 | Cabinetry & Trim
0197e29a-d4cd-7d3b-b1b1-f65b2bd20220 | 70.400 | Appliance Installation
0197e29a-d4cd-7d3b-b1b1-f65b2bd20220 | 70.500 | Plumbing Fixtures
0197e29a-d4cd-7d3b-b1b1-f65b2bd20220 | 70.600 | Electrical Fixtures
0197e29a-d4cd-7d3b-b1b1-f65b2bd20220 | 70.700 | HVAC Finish
0197e29a-d4cd-7d3b-b1b1-f65b2bd20220 | 70.800 | Rough Clean
0197e29a-d4cd-7d3b-b1b1-f65b2bd20220 | 70.900 | Drywall Touchup
0197e29a-d4cd-7d3b-b1b1-f65b2bd20220 | 70.1000 | Paint Touchup
0197e29a-d4cd-7d3b-b1b1-f65b2bd20220 | 70.1100 | Final Clean
0197e29a-d4cd-7d3b-b1b1-f65b2bd20220 | 80.100 | Landscaping
0197e29a-d4cd-7d3b-b1b1-f65b2bd20220 | 80.500 | Driveway
0197e29a-d4cd-7d3b-b1b1-f65b2bd20220 | 90.100 | Inspection (Final MEP Systems)
0197e29a-d4cd-7d3b-b1b1-f65b2bd20220 | 90.200 | Inspection (Final Building)
0197e29a-d4cd-7d3b-b1b1-f65b2bd20220 | 90.300 | Inspection (Final Site / Grading)
0197e29a-d4cd-7d3b-b1b1-f65b2bd20220 | 90.400 | Inspection (Certificate of Occupancy)