## task_groups
code | name | Description | sequence
10 | Pre-Construction | Design, permitting, budgeting, scheduling, and long-lead procurement activities before physical work begins | 1
20 | Site Preparation | Clearing, grading, erosion control, and temporary utility setup to prepare the site for foundation work. | 2
30 | Foundation | Excavation, formwork, reinforcement, and concrete work to establish the structural base of the building. | 3
40 | Framing | Construction of walls, floors, and roof structure to define the building’s shape and layout. | 4
50 | Exterior Envelope | Installation of sheathing, weather barrier, cladding, and exterior finishes to close in the structure. | 5
60 | MEP Roughs & Dry-In | Installation of mechanical, electrical, and plumbing systems (rough-ins), followed by insulation and drywall to dry-in the interior. | 6
70 | Interior Finishes | Completion of interior elements such as flooring, trim, painting, cabinetry, and final fixtures. | 7
80 | Landscaping & Exterior | Exterior site work including driveways, patios, landscaping, fencing, and exterior accessories. | 8
90 | Closeout | Final inspections, punch list completion, cleaning, and preparation for client turnover. | 9

## task_master
code | name | description | is_active | task_group_code | is_milestone
10.0100 | Architectural Design |  | TRUE | 10 | FALSE
10.0200 | Engineering Design (Structural/MEP) |  | TRUE | 10 | FALSE
10.0300 | Permits & Approvals |  | TRUE | 10 | FALSE
10.0400 | Budgeting & Financing Setup |  | TRUE | 10 | FALSE
10.0500 | Project Planning & Scheduling |  | TRUE | 10 | FALSE
10.0600 | Procurement of Long-Lead Materials |  | TRUE | 10 | FALSE
10.0700 | Inspection (Pre-Construction Site) |  | TRUE | 10 | TRUE
20.0100 | Site Survey & Soil Testing |  | TRUE | 20 | FALSE
20.0200 | Site Clearing & Excavation |  | TRUE | 20 | FALSE
20.0300 | Temporary Utilities Setup |  | TRUE | 20 | FALSE
20.0400 | Grading & Site Preparation |  | TRUE | 20 | FALSE
20.0500 | Erosion / Tree Control |  | TRUE | 20 | FALSE
20.0600 | Inspection (Erosion / Tree Protection) |  | TRUE | 20 | TRUE
30.0100 | Formwork for Foundation |  | TRUE | 30 | FALSE
30.0200 | Rebar Installation |  | TRUE | 30 | FALSE
30.0300 | Inspection (Footings) |  | TRUE | 30 | TRUE
30.0400 | Underground Plumbing |  | TRUE | 30 | FALSE
30.0500 | Inspection (Underground Plumbing) |  | TRUE | 30 | TRUE
30.0600 | Concrete Pouring (Footings & Slab) |  | TRUE | 30 | FALSE
30.0700 | Foundation Walls |  | TRUE | 30 | FALSE
30.0800 | Foundation Waterproofing |  | TRUE | 30 | FALSE
30.0900 | Inspection (Slab) |  | TRUE | 30 | TRUE
40.0100 | Framing – Walls & Floors |  | TRUE | 40 | FALSE
40.0200 | Framing – Roof |  | TRUE | 40 | FALSE
40.0300 | Inspection (Rough Framing) |  | TRUE | 40 | TRUE
50.0100 | Sheathing & Weather Barrier |  | TRUE | 50 | FALSE
50.0200 | Window Installation |  | TRUE | 50 | FALSE
50.0300 | Roofing Installation |  | TRUE | 50 | FALSE
50.0400 | Inspection (Roof Sheathing) |  | TRUE | 50 | TRUE
50.0500 | Trim Soffits and Facia |  | TRUE | 50 | FALSE
50.0600 | Exterior Cladding |  | TRUE | 50 | FALSE
50.0700 | Gutters |  | TRUE | 50 | FALSE
50.0800 | Exterior Painting |  | TRUE | 50 | FALSE
60.0100 | Plumbing Rough-in |  | TRUE | 60 | FALSE
60.0200 | Inspection (Rough Plumbing) |  | TRUE | 60 | TRUE
60.0300 | Electrical Rough-in |  | TRUE | 60 | FALSE
60.0400 | Inspection (Rough Electrical) |  | TRUE | 60 | TRUE
60.0500 | HVAC Rough-in |  | TRUE | 60 | FALSE
60.0600 | Inspection (Rough HVAC) |  | TRUE | 60 | TRUE
60.0700 | Fire Sprinkler Installation |  | TRUE | 60 | FALSE
60.0800 | Insulation |  | TRUE | 60 | FALSE
60.0900 | Inspection (Insulation) |  | TRUE | 60 | TRUE
60.1000 | Drywall Installation |  | TRUE | 60 | FALSE
60.1100 | Inspection (Energy Code Compliance) |  | TRUE | 60 | TRUE
70.0100 | Interior Painting |  | TRUE | 70 | FALSE
70.0200 | Flooring Installation |  | TRUE | 70 | FALSE
70.0300 | Interior Trim |  | TRUE | 70 | FALSE
70.0400 | Cabinets |  | TRUE | 70 | FALSE
70.0500 | Appliances |  | TRUE | 70 | FALSE
70.0600 | Plumbing Fixtures |  | TRUE | 70 | FALSE
70.0700 | Electrical Fixtures |  | TRUE | 70 | FALSE
70.0800 | HVAC Finish |  | TRUE | 70 | FALSE
70.0900 | Rough Clean |  | TRUE | 70 | FALSE
70.1000 | Drywall Touchup |  | TRUE | 70 | FALSE
70.1100 | Paint Touchup |  | TRUE | 70 | FALSE
70.1200 | Final Clean |  | TRUE | 70 | FALSE
80.0100 | Landscaping |  | TRUE | 80 | FALSE
80.0200 | Patios |  | TRUE | 80 | FALSE
80.0300 | Fencing |  | TRUE | 80 | FALSE
80.0400 | Pool |  | TRUE | 80 | FALSE
80.0500 | Driveway |  | TRUE | 80 | FALSE
90.0100 | Inspection (Final MEP Systems) |  | TRUE | 90 | TRUE
90.0200 | Inspection (Final Building) |  | TRUE | 90 | TRUE
90.0300 | Inspection (Final Site / Grading) |  | TRUE | 90 | TRUE
90.0400 | Inspection (Certificate of Occupancy) |  | TRUE | 90 | TRUE

## template_tasks
unit_name | version | task_code | name | description
Tempest | 1 | 10.0100 | Architectural Design
Tempest | 1 | 10.0200 | Engineering Design (Structural/MEP)
Tempest | 1 | 10.0300 | Permits & Approvals
Tempest | 1 | 10.0400 | Budgeting & Financing Setup
Tempest | 1 | 10.0500 | Project Planning & Scheduling
Tempest | 1 | 10.0600 | Procurement of Long-Lead Materials
Tempest | 1 | 10.0700 | Inspection (Pre-Construction Site)
Tempest | 1 | 20.0100 | Site Survey & Soil Testing
Tempest | 1 | 20.0200 | Site Clearing & Excavation
Tempest | 1 | 20.0300 | Temporary Utilities Setup
Tempest | 1 | 20.0400 | Grading & Site Preparation
Tempest | 1 | 20.0500 | Erosion / Tree Control
Tempest | 1 | 20.0600 | Inspection (Erosion / Tree Protection)
Tempest | 1 | 30.0100 | Formwork for Foundation
Tempest | 1 | 30.0200 | Rebar Installation
Tempest | 1 | 30.0300 | Inspection (Footings)
Tempest | 1 | 30.0400 | Underground Plumbing
Tempest | 1 | 30.0500 | Inspection (Underground Plumbing)
Tempest | 1 | 30.0600 | Concrete Pouring (Footings & Slab)
Tempest | 1 | 30.0700 | Foundation Walls
Tempest | 1 | 30.0800 | Foundation Waterproofing
Tempest | 1 | 30.0900 | Inspection (Slab)
Tempest | 1 | 40.0100 | Framing – Walls & Floors
Tempest | 1 | 40.0200 | Framing – Roof
Tempest | 1 | 40.0300 | Inspection (Rough Framing)
Tempest | 1 | 50.0100 | Sheathing & Weather Barrier
Tempest | 1 | 50.0200 | Window Installation
Tempest | 1 | 50.0300 | Roofing Installation
Tempest | 1 | 50.0400 | Inspection (Roof Sheathing)
Tempest | 1 | 50.0500 | Trim Soffits and Facia
Tempest | 1 | 50.0600 | Exterior Cladding
Tempest | 1 | 50.0700 | Gutters
Tempest | 1 | 50.0800 | Exterior Painting
Tempest | 1 | 60.0100 | Plumbing Rough-in
Tempest | 1 | 60.0200 | Inspection (Rough Plumbing)
Tempest | 1 | 60.0300 | Electrical Rough-in
Tempest | 1 | 60.0400 | Inspection (Rough Electrical)
Tempest | 1 | 60.0500 | HVAC Rough-in
Tempest | 1 | 60.0600 | Inspection (Rough HVAC)
Tempest | 1 | 60.0700 | Fire Sprinkler Installation
Tempest | 1 | 60.0800 | Insulation
Tempest | 1 | 60.0900 | Inspection (Insulation)
Tempest | 1 | 60.1000 | Drywall Installation
Tempest | 1 | 60.1100 | Inspection (Energy Code Compliance)
Tempest | 1 | 70.0100 | Interior Painting
Tempest | 1 | 70.0200 | Flooring Installation
Tempest | 1 | 70.0300 | Interior Trim
Tempest | 1 | 70.0400 | Cabinets
Tempest | 1 | 70.0500 | Appliances
Tempest | 1 | 70.0600 | Plumbing Fixtures
Tempest | 1 | 70.0700 | Electrical Fixtures
Tempest | 1 | 70.0800 | HVAC Finish
Tempest | 1 | 70.0900 | Rough Clean
Tempest | 1 | 70.1000 | Drywall Touchup
Tempest | 1 | 70.1100 | Paint Touchup
Tempest | 1 | 70.1200 | Final Clean
Tempest | 1 | 80.0100 | Landscaping
Tempest | 1 | 80.0500 | Driveway
Tempest | 1 | 90.0100 | Inspection (Final MEP Systems)
Tempest | 1 | 90.0200 | Inspection (Final Building)
Tempest | 1 | 90.0300 | Inspection (Final Site / Grading)
Tempest | 1 | 90.0400 | Inspection (Certificate of Occupancy)

## template_cost_items
unit_name | unit_version | task_code | parent_code | item_code | cost_class | cost_source | description | quantity | unit_cost
Tempest | 1 | 10.0100 |  |  | labor | turnkey | Custom architectural plans and blueprints for the home | 1 | 24500
Tempest | 1 | 10.0200 |  |  | labor | turnkey | Structural and MEP (mechanical electrical plumbing) engineering plans | 1 | 17500
Tempest | 1 | 10.0300 |  |  | labor | turnkey | Obtaining necessary building permits and approvals | 1 | 1500
Tempest | 1 | 10.0400 |  |  | labor | turnkey | Financial planning and loan setup for project funding | 1 | 2000
Tempest | 1 | 10.0500 |  |  | labor | turnkey | Creating project timeline and coordination schedule | 1 | 3000
Tempest | 1 | 10.0600 |  |  | material | turnkey | Sourcing long-lead items like windows and doors | 1 | 5000
Tempest | 1 | 10.0700 |  |  | labor | turnkey | Initial site inspection for compliance and readiness | 1 | 500
Tempest | 1 | 20.0100 |  |  | labor | turnkey | Land surveying and soil analysis for foundation design | 1 | 1500
Tempest | 1 | 20.0200 |  |  | material | turnkey | Removing vegetation and excavating for foundation | 1 | 1500
Tempest | 1 | 20.0200 |  |  | labor | turnkey | Removing vegetation and excavating for foundation | 1 | 1500
Tempest | 1 | 20.0300 |  |  | material | turnkey | Install temporary power water and sanitation | 1 | 1000
Tempest | 1 | 20.0300 |  |  | labor | turnkey | Install temporary power water and sanitation | 1 | 1000
Tempest | 1 | 20.0400 |  |  | material | turnkey | Leveling and preparing site for construction | 1 | 1250
Tempest | 1 | 20.0400 |  |  | labor | turnkey | Leveling and preparing site for construction | 1 | 1250
Tempest | 1 | 20.0500 |  |  | material | turnkey | Install erosion control measures and tree protection | 1 | 750
Tempest | 1 | 20.0500 |  |  | labor | turnkey | Install erosion control measures and tree protection | 1 | 750
Tempest | 1 | 20.0600 |  |  | labor | turnkey | Inspection of erosion and tree protection measures | 1 | 500
Tempest | 1 | 30.0100 |  |  | material | turnkey | Constructing forms for concrete footings and slab | 1 | 1500
Tempest | 1 | 30.0100 |  |  | labor | turnkey | Constructing forms for concrete footings and slab | 1 | 1500
Tempest | 1 | 30.0200 |  |  | material | turnkey | Install reinforcing steel bars for foundation | 1 | 1750
Tempest | 1 | 30.0200 |  |  | labor | turnkey | Install reinforcing steel bars for foundation | 1 | 750
Tempest | 1 | 30.0300 |  |  | labor | turnkey | Inspection of footings before concrete pour | 1 | 500
Tempest | 1 | 30.0400 |  |  | material | turnkey | Install underground plumbing for drainage and supply | 1 | 2000
Tempest | 1 | 30.0400 |  |  | labor | turnkey | Install underground plumbing for drainage and supply | 1 | 2000
Tempest | 1 | 30.0500 |  |  | labor | turnkey | Inspection of underground plumbing installation | 1 | 500
Tempest | 1 | 30.0600 |  |  | material | turnkey | Pouring concrete for footings and slab foundation | 1 | 7920
Tempest | 1 | 30.0600 |  |  | labor | turnkey | Pouring concrete for footings and slab foundation | 1 | 5280
Tempest | 1 | 30.0700 |  |  | material | turnkey | Constructing concrete foundation walls | 1 | 2500
Tempest | 1 | 30.0700 |  |  | labor | turnkey | Constructing concrete foundation walls | 1 | 2500
Tempest | 1 | 30.0800 |  |  | material | turnkey | Applying waterproofing to foundation walls | 1 | 2970
Tempest | 1 | 30.0800 |  |  | labor | turnkey | Applying waterproofing to foundation walls | 1 | 2970
Tempest | 1 | 30.0900 |  |  | labor | turnkey | Inspection of slab after pouring | 1 | 500
Tempest | 1 | 40.0100 |  |  | material | turnkey | 1st Floor Framing | 1 | 7500
Tempest | 1 | 40.0100 |  |  | material | turnkey | 2nd Floor Framing | 1 | 7500
Tempest | 1 | 40.0100 |  |  | material | turnkey | 3rd Floor Framing | 1 | 7500
Tempest | 1 | 40.0100 |  |  | labor | turnkey | 1st Floor Framing | 1 | 7500
Tempest | 1 | 40.0100 |  |  | labor | turnkey | 2nd Floor Framing | 1 | 7500
Tempest | 1 | 40.0100 |  |  | labor | turnkey | 3rd Floor Framing | 1 | 7500
Tempest | 1 | 40.0200 |  |  | material | turnkey | Constructing roof trusses and framing | 1 | 5000
Tempest | 1 | 40.0200 |  |  | labor | turnkey | Constructing roof trusses and framing | 1 | 5000
Tempest | 1 | 40.0300 |  |  | labor | turnkey | Inspection of framing for structural integrity | 1 | 500
Tempest | 1 | 50.0100 |  |  | material | turnkey | Install exterior sheathing and weather-resistant barrier | 1 | 3000
Tempest | 1 | 50.0100 |  |  | labor | turnkey | Install exterior sheathing and weather-resistant barrier | 1 | 3000
Tempest | 1 | 50.0200 |  |  | material | turnkey | Install mid-range windows | 1 | 4800
Tempest | 1 | 50.0200 |  |  | labor | turnkey | Install mid-range windows | 1 | 3200
Tempest | 1 | 50.0300 |  |  | material | turnkey | Install asphalt shingle roofing | 1 | 4950
Tempest | 1 | 50.0300 |  |  | labor | turnkey | Install asphalt shingle roofing | 1 | 4950
Tempest | 1 | 50.0400 |  |  | labor | turnkey | Inspection of roof sheathing installation | 1 | 500
Tempest | 1 | 50.0500 |  |  | material | turnkey | Install exterior trim | 1 | 1700
Tempest | 1 | 50.0500 |  |  | labor | turnkey | Install exterior trim | 1 | 2250
Tempest | 1 | 50.0600 |  |  | material | turnkey | Install fiber cement siding on exterior walls | 1 | 5500
Tempest | 1 | 50.0600 |  |  | labor | turnkey | Install fiber cement siding on exterior walls | 1 | 5500
Tempest | 1 | 50.0700 |  |  | material | turnkey | Install gutters | 1 | 1000
Tempest | 1 | 50.0700 |  |  | labor | turnkey | Install gutters | 1 | 600
Tempest | 1 | 50.0800 |  |  | material | turnkey | Paint home exterior | 1 | 3000
Tempest | 1 | 50.0800 |  |  | labor | turnkey | Paint home exterior | 1 | 3000
Tempest | 1 | 60.0100 |  |  | material | turnkey | Install rough-in plumbing pipes and vents | 1 | 4000
Tempest | 1 | 60.0100 |  |  | labor | turnkey | Install rough-in plumbing pipes and vents | 1 | 4000
Tempest | 1 | 60.0200 |  |  | labor | turnkey | Inspection of rough-in plumbing | 1 | 500
Tempest | 1 | 60.0300 |  |  | material | turnkey | Install electrical wiring and boxes | 1 | 4400
Tempest | 1 | 60.0300 |  |  | labor | turnkey | Install electrical wiring and boxes | 1 | 4400
Tempest | 1 | 60.0400 |  |  | labor | turnkey | Inspection of rough-in electrical | 1 | 500
Tempest | 1 | 60.0500 |  |  | material | turnkey | Install HVAC ductwork and rough-in components | 1 | 3500
Tempest | 1 | 60.0500 |  |  | labor | turnkey | Install HVAC ductwork and rough-in components | 1 | 3500
Tempest | 1 | 60.0600 |  |  | labor | turnkey | Inspection of HVAC rough-in | 1 | 500
Tempest | 1 | 60.0700 |  |  | material | turnkey | Install fire sprinkler system | 1 | 2000
Tempest | 1 | 60.0700 |  |  | labor | turnkey | Install fire sprinkler system | 1 | 2000
Tempest | 1 | 60.0800 |  |  | material | turnkey | Install fiberglass batt insulation | 1 | 2000
Tempest | 1 | 60.0800 |  |  | labor | turnkey | Install fiberglass batt insulation | 1 | 2000
Tempest | 1 | 60.0900 |  |  | labor | turnkey | Inspection of insulation installation | 1 | 500
Tempest | 1 | 60.0100 |  |  | material | turnkey | Install and taping drywall | 1 | 4000
Tempest | 1 | 60.0100 |  |  | labor | turnkey | Install and taping drywall | 1 | 4000
Tempest | 1 | 60.1100 |  |  | labor | turnkey | Inspection for energy code compliance | 1 | 500
Tempest | 1 | 70.0100 |  |  | material | turnkey | Applying interior paint to walls and ceilings | 1 | 3000
Tempest | 1 | 70.0100 |  |  | labor | turnkey | Applying interior paint to walls and ceilings | 1 | 3000
Tempest | 1 | 70.0200 |  |  | material | turnkey | Install mid-range flooring (e.g. hardwood tile) | 1 | 6600
Tempest | 1 | 70.0200 |  |  | labor | turnkey | Install mid-range flooring (e.g. hardwood tile) | 1 | 4400
Tempest | 1 | 70.0300 |  |  | material | turnkey | Install interior trim | 1 | 3200
Tempest | 1 | 70.0300 |  |  | labor | turnkey | Install interior trim | 1 | 4800
Tempest | 1 | 70.0400 |  |  | material | turnkey | Kitchen Cabinets | 1 | 4000
Tempest | 1 | 70.0500 |  |  | material | turnkey | Install kitchen and laundry appliances | 1 | 6400
Tempest | 1 | 70.0500 |  |  | labor | turnkey | Install kitchen and laundry appliances | 1 | 1600
Tempest | 1 | 70.0600 |  |  | material | turnkey | Install sinks faucets and toilets | 1 | 3000
Tempest | 1 | 70.0600 |  |  | labor | turnkey | Install sinks faucets and toilets | 1 | 2000
Tempest | 1 | 70.0700 |  |  | material | turnkey | Install lighting and electrical fixtures | 1 | 3000
Tempest | 1 | 70.0700 |  |  | labor | turnkey | Install lighting and electrical fixtures | 1 | 2000
Tempest | 1 | 70.0800 |  |  | material | turnkey | Install HVAC units and final components | 1 | 2000
Tempest | 1 | 70.0800 |  |  | labor | turnkey | Install HVAC units and final components | 1 | 2000
Tempest | 1 | 70.0900 |  |  | labor | turnkey | Initial cleanup after rough-in phases | 1 | 2000
Tempest | 1 | 70.0100 |  |  | material | turnkey | Touching up drywall imperfections | 1 | 750
Tempest | 1 | 70.0100 |  |  | labor | turnkey | Touching up drywall imperfections | 1 | 750
Tempest | 1 | 70.1100 |  |  | material | turnkey | Touching up interior paint | 1 | 750
Tempest | 1 | 70.1100 |  |  | labor | turnkey | Touching up interior paint | 1 | 750
Tempest | 1 | 70.1200 |  |  | labor | turnkey | Final cleanup before occupancy | 1 | 2000
Tempest | 1 | 80.0100 |  |  | material | turnkey | Install sod plants and basic landscaping | 1 | 2500
Tempest | 1 | 80.0100 |  |  | labor | turnkey | Install sod plants and basic landscaping | 1 | 2500
Tempest | 1 | 80.0500 |  |  | material | turnkey | Install concrete driveway | 1 | 4000
Tempest | 1 | 80.0500 |  |  | labor | turnkey | Install concrete driveway | 1 | 4000
Tempest | 1 | 90.0100 |  |  | labor | turnkey | Final inspection of MEP systems | 1 | 500
Tempest | 1 | 90.0200 |  |  | labor | turnkey | Final building inspection | 1 | 500
Tempest | 1 | 90.0300 |  |  | labor | turnkey | Final site and grading inspection | 1 | 500
Tempest | 1 | 90.0400 |  |  | labor | turnkey | Inspection for certificate of occupancy | 1 | 500